## Slide 1
Weekly Report
Management Information System Division

## Slide 3
LM1 (Feb. 14 – 19, 2022)
CIS v3 – Accounting (Internal Project)
Module | WBS | Weight for the Week (Dec 7 to 12) | Completion for the week | Score
Request for Payment | Additional Filters | 5 | 100.00% | 5
 | Add loaders | 8 | 100.00% | 8
 | Add details of profit analysis | 8 | 100.00% | 8
 | Add payee selection on display name | 5 | 100.00% | 5
 | Add PDF in attachment | 5 | 100.00% | 5
 | Fix quality of image in attach | 5 | 100.00% | 5
Canvassing Management | Additional Filters | 5 | 100.00% | 5
PO Management | Add template in printing | 5 | 100% | 5
Budget LOA | Condition in view for users | 8 | 100% | 8
Budget Plan Report | Sticky Header | 6 | 100% | 6
Liquidation | Build Page | 15 | 20% | 3
Supplier Ledger | Build Page | 10 | 40% | 4
Check Voucher | Create / List for vouchers | 10 | 85% | 8.5
Bank Validation / Cash flow | Build Page | 10 | 0% | 0
SCORE : 70.5

## Slide 4
LM1 (Feb. 14 – 19, 2022)
CaPEx Accounting App - (Internal Project)
SCORE : 80
Module | WBS | Weight for the Week (Dec 7 to 12) | Completion for the week | Score
Liquidation (Attach) | Login screen: Create Login template | 5 | 100.00% | 5
 | Login screen: Add - login validation | 5 | 100.00% | 5
 | Login screen: Add - trigger show/hide password | 10 | 100.00% | 10
 | Login screen: Add - loading and dialog message | 10 | 100.00% | 10
 | Home screen : Add - clickable action button | 10 | 100.00% | 10
 | Home screen : Add - navigation for page attachment | 10 | 100.00% | 10
 | Home screen : Add - search input for filtering | 10 | 100.00% | 10
 | Create API | 20 | 50% | 10
Request for payment | Create API | 20 | 50% | 10